# Solimed Study Tracking Enhancement — Project Charter

Project Name: Solimed Study Tracking — Enhancement & International Expansion Project Sponsor: Ivan Kruljac (Solimed) Project Manager: TBD (Pivot) Technical Lead: TBD (Pivot) Charter Version: 1.0 — DRAFT Date: 2026-04-02 Status: Pending signature

## 1. Project Purpose & Justification

Solimed operates a purpose-built SMO (Site Management Organization) platform — Study Tracking — that manages clinical trial operations across 2 sites in Croatia (Solimed Clinic and Medico RI). The platform currently manages 321 active enrolled patients, 15+ CRO relationships, and €2.1M in tracked financial backlog across studies running through 2032.

The platform was built deliberately over 3+ years and is working well at its current scale. It is now approaching the ceiling of its Power Apps architecture — a ceiling that will prevent international expansion, third-party integrations, and enterprise-grade security and compliance.

The purpose of this project is to: 1. Resolve confirmed operational gaps in the current platform (Phase 1) 2. Re-architect the foundation for scale, security, and multi-tenancy (Phase 2) 3. Expand the platform to new international markets (Phase 3) 4. Integrate the platform with the broader clinical trial ecosystem (Phase 4) 5. Productize the platform as a scalable SaaS offering (Phase 5)

Business justification: - The €2.1M backlog figure is currently unreliable due to multi-arm study inflation - Investigator fee calculations are incomplete without working hours differentiation - Screen fail revenue recognition is untracked — creating billing exposure - International expansion is commercially blocked by the current single-tenant, single-locale architecture - The SaaS opportunity in the CTMS/SMO space (€3.5B market, 13% CAGR) is directly accessible to Solimed if the platform is productized

## 2. Project Scope

### In Scope

Phase 1 — Quick Wins (Months 1–3): - Working hours flag and fee recalculation engine - Multi-arm study arm assignment and backlog correction - Screen fail allotment tracking and revenue recognition split - Automated investigator specification generation and sending - Coordinator to-do dashboard and visit tolerance warnings - Bulk visit status operations - Study progress summary cards - Site budget fix, override, and lock/unlock controls - Demand and time tracking with normita baseline - Study show/stop lifecycle controls with auto-generated stop reports - Overall budget, revenue, and normita Power BI dashboard - Revenue status ladder and cash flow forecast dashboards - Backlog quality score dashboard

Phase 2 — Platform Hardening (Months 3–5): - REST API layer (all core entities) - Multi-tenant data model with country/site isolation - 6-tier RBAC implementation - PII audit logging (GDPR-ready) - Azure infrastructure setup (Dev, Staging, Production) - CI/CD pipeline and automated test suite

Phase 3 — International Expansion (Months 6–9): - i18n/localization framework - Multi-currency engine with FX rates - Country-specific regulatory configuration - Data residency per country (Azure region) - Country onboarding playbook - First non-Croatia site live

Phase 4 — Ecosystem Integration (Months 10–14): - EDC bidirectional sync (minimum 1 CRO system) - Automated invoicing engine - Mobile application (iOS + Android) - Document management system

Phase 5 — SaaS Productization (Months 15–20): - Self-service tenant onboarding - Subscription billing engine - CRO network portal - AI-driven predictive features

### Explicitly Out of Scope

- Patient-facing portal, patient recruitment engine, or patient communication system (CRO/sponsor domain)

- Electronic Data Capture (EDC) — Solimed does not and will not replicate clinical data from CRO EDC systems

- Source documentation digitalization — paper source docs remain per CRO advisory

- Replacement of Power BI reporting with a different BI tool

- Any changes to CRO-owned systems or sponsor systems

- Clinical data entry or modification of any kind

- 21 CFR Part 11 compliance (unless a US expansion is formally scoped in Phase 3+)

- Hardware procurement or on-premise infrastructure

### Assumptions

- Mladen Geng is available for a minimum of 2 days/week during Sprints 1–2 for knowledge transfer

- Ivan Kruljac and Drew Domescik are available for bi-weekly sprint reviews (1 hour each)

- At least 2–3 site coordinators are available for usability testing in Phase 1

- Solimed has or will provision necessary Azure licenses and subscriptions

- The existing Power Apps/Dataverse environment remains operational throughout Phase 1–2

- All existing data in the platform is accurate and suitable for migration (data quality to be validated in Sprint 1)

- Solimed has legal authority to store patient data (anonymized IDs) in the current platform

### Constraints

- Coordinators cannot be disrupted during active study periods — production releases must be scheduled during low-activity windows

- Investigator payment specifications must continue to run correctly throughout all phases — no disruption to the monthly payment cycle

- Power Apps must remain the UI through Phase 2 at minimum (no big-bang rewrite)

- All development must remain within the Microsoft Azure ecosystem

## 3. Project Objectives & Success Criteria

| Objective | Measurable Success Criterion |
| --- | --- |
| Fix financial forecast integrity | Multi-arm backlog inflation resolved; €2.1M figure reconciled to arm-assigned value within 5% |
| Fix fee calculation accuracy | Working hours flag live; zero investigator payment disputes attributable to hours-type calculation errors for 3 consecutive months |
| Automate investigator specs | Monthly specification emails sending automatically; finance team spends <30 minutes/month on investigator payment prep vs. current baseline |
| Establish API layer | API v1 live with >80% test coverage; all Phase 1 Power Apps screens reading/writing through API |
| Achieve multi-tenant architecture | Second site or country added to platform without schema changes |
| First international expansion | First non-Croatia site live, processing real studies within Phase 3 timeline |
| Revenue intelligence | Drew Domescik confirms the backlog quality dashboard and cash flow forecast meet CFO-level reporting needs |
| Platform NPS | Coordinator NPS ≥40 post Phase 1 launch |

## 4. Stakeholders

| Name | Organization | Role | Engagement Level |
| --- | --- | --- | --- |
| Ivan Kruljac | Solimed | Project Sponsor / Business Owner | High — weekly involvement |
| Drew Domescik | Advisor | CFO Advisor / Financial Feature Sponsor | Medium — sprint reviews + financial UAT |
| Mladen Geng | Solimed | Current Developer / Domain Expert | High — Sprints 1–2; then as-needed |
| Site Coordinators (2–3) | Solimed | End Users — primary app users | Medium — usability testing and UAT |
| Finance Role (TBD) | Solimed | Billing and investigator payment owner | Medium — billing workflow UAT |
| Site Managers (TBD) | Solimed | Study setup and budget configuration | Low-Medium — admin feature UAT |
| Pivot PM | Pivot | Delivery Owner | High — daily |
| Pivot Technical Lead | Pivot | Architecture and development | High — daily |
| Pivot BI Engineer | Pivot | Power BI development | High — Sprint 6+ |

## 5. High-Level Timeline

| Phase | Duration | Target Start | Target End |
| --- | --- | --- | --- |
| Phase 1 — Quick Wins | 3 months | Month 1 | Month 3 |
| Phase 2 — Platform Hardening | 3 months | Month 3 | Month 5 |
| Phase 3 — International Expansion | 4 months | Month 6 | Month 9 |
| Phase 4 — Ecosystem Integration | 5 months | Month 10 | Month 14 |
| Phase 5 — SaaS Productization | 6 months | Month 15 | Month 20 |
| Total | 20 months |  |  |

## 6. Budget Authorization

| Phase | Budget Range | Authorization |
| --- | --- | --- |
| Phase 1 | €38,000 – €50,000 | Required before Sprint 1 start |
| Phase 2 | €72,000 – €90,000 | Required before Phase 2 start |
| Phase 3 | €96,000 – €120,000 | Required before Phase 3 start |
| Phase 4 | €130,000 – €160,000 | Required before Phase 4 start |
| Phase 5 | €140,000 – €175,000 | Required before Phase 5 start |
| Total | €476,000 – €595,000 |  |

Budget for each phase is authorized separately. Solimed is not committed to subsequent phases by authorizing Phase 1.

Infrastructure costs (Azure, Power BI Embedded, third-party APIs) are billed directly to Solimed and are not included above. Estimated at €500–€2,000/month depending on phase.

## 7. Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Mladen unavailable for knowledge transfer | Medium | Critical | Prioritize in Sprint 1; record all sessions |
| Power Apps limitations block Phase 1 features | Medium | High | Assess feasibility Sprint 1; parallel API track if needed |
| Scope creep across phases | High | Medium | Formal change control; all additions require written approval |
| Data quality issues discovered during migration | Medium | High | Data audit Sprint 1 before any migration begins |
| Coordinator resistance to new features | Medium | Medium | Paced rollout per Ivan’s preference; change management plan |
| Regulatory requirements unknown for target expansion country | High | High | Regulatory review begins Phase 2; legal counsel engaged |
| Clinical data privacy breach | Low | Critical | Security audit before Phase 3; penetration testing |

## 8. Governance

Decision authority: - Feature scope changes: Ivan Kruljac (Solimed) + Pivot PM joint approval - Technical architecture: Pivot Technical Lead with Ivan review - Budget changes >5%: Ivan Kruljac written approval - Production deployments: Pivot PM + Solimed written sign-off

Escalation path: Pivot PM → Ivan Kruljac → Drew Domescik (if financial/strategic escalation)

Change control: All scope changes submitted in writing. Pivot assesses impact within 3 business days. Changes >16 hours require a formal change order signed by Ivan Kruljac before work begins.

## 9. Charter Approval

By signing below, both parties agree to the project purpose, scope, objectives, timeline, and governance described in this charter. This charter authorizes Phase 1 work to begin.

|  | Solimed | Pivot |
| --- | --- | --- |
| Signed | _________________ | _________________ |
| Name | Ivan Kruljac |  |
| Title | Co-founder |  |
| Date |  |  |

This charter authorizes Phase 1 only. Subsequent phases require separate budget authorization and updated scope confirmation before commencement.