# Meridian — Product Development PM Plan

## Unified Clinical Trial Intelligence Platform

Product: Meridian (by Pivot) Document Type: Product PM Plan Prepared by: Pivot Date: 2026-04-02 Version: 1.0 Horizon: 24 months (Months 1–24)

## 1. Product Overview

Meridian is a unified clinical trial intelligence platform built across five layers:

| Layer | Name | Core Capability |
| --- | --- | --- |
| 5 | AI Intelligence | Predictive patient scoring, dropout risk, revenue forecasting, protocol deviation detection |
| 4 | Communication Hub | AI voice/SMS/video, real-time coordinator coaching, sentiment analysis, call summaries |
| 3 | Clinical Operations | Study/visit management, eSource, eConsent, regulatory binder, payment configuration |
| 2 | Payment Engine | Investigator fees, CRO invoicing, patient reimbursements, cash flow forecasting |
| 1 | Data Ingestion Hub | EHR (FHIR), EDC sync, lab systems, wearables, claims data, registries |

Design partner / first customer: Solimed (Croatia-based SMO, 2 sites, 321 active patients, 15+ CROs) Market target: SMOs and independent research sites managing 5–500 active studies Year 3 ARR target: €600K+ (50 sites × €1,000/month average)

## 2. Development Philosophy

Build with, not for. Solimed is not just a client — they are the development partner. Every feature built in Phase 1 is validated against real clinical trial operations before we declare it market-ready.

Layer-first, not feature-first. Each layer must be stable before the layer above it is built. You cannot build AI predictions (Layer 5) without reliable data (Layer 1) and a complete operational record (Layers 2–3).

Ship working software every sprint. No sprint ends without a working, demonstrable increment. Coordinators and investigators use what we build in production — not in a demo environment.

Solimed’s constraints are the platform’s constraints. If something is too complex for Solimed’s coordinators, it’s too complex for any site. Build for the least-technical user on the most demanding protocol.

## 3. Phases Overview

| Phase | Name | Duration | Primary Deliverable |
| --- | --- | --- | --- |
| Phase 0 | Foundation | Weeks 1–4 | Team, tooling, access, architecture decisions |
| Phase 1 | Solimed Build | Months 1–9 | Layers 1–5 built for Solimed; platform validated in production |
| Phase 2 | Second Site | Months 10–15 | Multi-tenancy live; second SMO onboarded; AI trained on real data |
| Phase 3 | Market Launch | Months 16–24 | Self-serve onboarding; subscription billing; 5+ sites live |

## 4. Phase 0 — Foundation (Weeks 1–4)

Goal: Set the team up to build. No features ship in Phase 0 — only infrastructure, access, and decisions.

### Week 1: Access & Discovery

| Task | Owner | Done When |
| --- | --- | --- |
| NDA signed with Solimed | Pivot PM | Signed document on file |
| Phase 1 SOW signed | Pivot PM + Ivan Kruljac | Signed SOW on file |
| Power Apps read access provisioned for Pivot | Mladen Geng | Pivot can view all screens and data |
| Power BI workspace access provisioned | Mladen Geng | Pivot BI engineer can open data model |
| Dataverse read access or full export | Mladen Geng | Schema documented |
| Azure subscription confirmed or provisioned | Ivan Kruljac | Azure tenant ID shared with Pivot |
| Clarify WTE Solutions engagement status | Ivan Kruljac | Written confirmation of status |
| GitHub repo created: pivot-meridian | Pivot Tech Lead | Repo live, branch strategy defined |
| Linear / Jira project created | Pivot PM | Backlog created; all team members invited |
| Communication channels set up (Teams/Slack) | Pivot PM | Channels live; Solimed team added |

### Week 2: Architecture Decision Records (ADRs)

The following decisions must be made and documented before a line of code is written:

| Decision | Options | Deadline |
| --- | --- | --- |
| API language: Node.js (Fastify) vs. Python (FastAPI) | Performance vs. ML team preference | Week 2 |
| Database: PostgreSQL vs. Azure SQL vs. split | Cost, HIPAA, team familiarity | Week 2 |
| Patient profile store: MongoDB vs. PostgreSQL JSON | Flexibility vs. consistency | Week 2 |
| Auth provider: Auth0 vs. Azure AD B2C | Cost at scale, Microsoft ecosystem | Week 2 |
| Communications: Twilio vs. Azure Communication Services | HIPAA BAA, feature set, cost | Week 2 |
| FHIR layer: Azure Health Data Services vs. build own | Cost vs. control | Week 2 |
| Frontend: Next.js only vs. Next.js + React Native | Mobile priority in Phase 1 | Week 2 |
| BI reporting: Power BI Embedded vs. build custom | Solimed compatibility, cost | Week 2 |

### Week 3: Data Model & Knowledge Transfer

| Task | Owner | Done When |
| --- | --- | --- |
| Full Solimed data model documented (all Dataverse tables, relationships, field types) | Pivot + Mladen | ERD diagram approved |
| All Power Apps business logic documented (fee calculations, visit status rules, auto-scheduling logic) | Pivot + Mladen | Logic document reviewed by Ivan |
| All Power BI DAX measures documented | Pivot BI Engineer + Mladen | All 30+ measures documented |
| Known workarounds and edge cases documented | Mladen | List reviewed by Ivan |
| Test data vs. production data identified and flagged | Mladen | Clean data baseline established |
| Data quality audit: null rates, duplicates, value distributions | Pivot + Mladen | Audit report complete |
| Power Apps staging environment created | Mladen + Pivot | Staging env live and accessible |

### Week 4: Environment Setup & Sprint 1 Planning

| Task | Owner | Done When |
| --- | --- | --- |
| Azure Dev + Staging + Prod environments provisioned | Pivot DevOps | All 3 environments live |
| CI/CD pipeline: GitHub Actions → Staging | Pivot Tech Lead | Auto-deploy on merge to main |
| Database schemas created (Dev) | Pivot Tech Lead | Migration scripts run cleanly |
| API skeleton running (health check endpoint live) | Pivot Tech Lead | /health returns 200 |
| Auth0 / Azure AD B2C tenant configured | Pivot Tech Lead | Test user can log in |
| Sprint 1 backlog groomed and estimated | Pivot PM + team | All Sprint 1 stories estimated and ready |
| Kickoff meeting with Ivan + Drew | Pivot PM | Demo of Phase 0 deliverables; Sprint 1 plan reviewed |

## 5. Phase 1 — Solimed Build (Months 1–9 / Sprints 1–18)

Goal: Build a complete, production-grade version of Meridian using Solimed as the design partner. By the end of Phase 1, Solimed is fully off Power Apps and running on Meridian. All 5 layers are functional for Solimed’s specific use case.

### Sprint Cadence

- 2-week sprints

- Sprint planning: Monday Week 1

- Mid-sprint check-in: Wednesday Week 1

- Sprint review / demo to Ivan + Drew: Friday Week 2

- Retrospective: Internal Pivot only, Friday Week 2

### Layer 1 — Data Ingestion Hub (Sprints 1–4)

Goal: Establish the authoritative data store. Migrate Solimed from Power Apps/Dataverse to Meridian’s PostgreSQL backend.

| Sprint | Deliverables |
| --- | --- |
| Sprint 1 | Database schema v1: Studies, Site Studies, Patients, Visits, Investigators, Budgets — modelled from Solimed data model ERD |
| Sprint 1 | Data migration script: full Dataverse export → PostgreSQL import with validation |
| Sprint 2 | Migration dry-run on staging: all Solimed data migrated; record counts match; no data loss |
| Sprint 2 | EDC sync adapter v1: read-only pull of visit status from one CRO’s EDC system (pilot CRO selected with Ivan) |
| Sprint 3 | Multi-tenant schema: tenant_id + country_id + site_id on all tables; row-level security enforced |
| Sprint 3 | Excel time tracking migration: import historical time tracking data from Excel into PostgreSQL time_entries table |
| Sprint 4 | FHIR adapter stub: Azure Health Data Services provisioned; basic FHIR R4 patient resource read (for Phase 2 EHR integration) |
| Sprint 4 | Data ingestion API: REST endpoints for external data push; webhook receiver for EDC event notifications |

Milestone M1.1: All Solimed data live in Meridian PostgreSQL; Power Apps reads from Meridian API (not Dataverse) — end Sprint 4

### Layer 2 — Payment Engine (Sprints 3–8)

Goal: Full investigator fee management, CRO invoicing, patient reimbursements, and cash flow forecasting — replacing Solimed’s current manual billing process entirely.

| Sprint | Deliverables |
| --- | --- |
| Sprint 3 | Investigator fee engine v1: PI fee, PI cut %, sub-investigator splits, referral doctor fee — all calculated from API (not Power Apps formulas) |
| Sprint 4 | Working hours flag: in-hours vs. after-hours toggle on visit record; fee engine applies correct rate per flag |
| Sprint 5 | Monthly investigator specification generator: auto-generate PDF spec per investigator from approved visits for selected month |
| Sprint 5 | Automated spec delivery: email each investigator their monthly specification on configured schedule; finance review gate (approve before send / auto-send) |
| Sprint 6 | Screen fail allotment engine: contractual allotment per study; running counter; over-allotment flag in P&L; billable vs. non-billable split |
| Sprint 6 | Revenue status ladder: Scheduled → Earned → Approved → Invoiced → Received → Written Off — all visit revenue classified at all times |
| Sprint 7 | Invoice generation: auto-generate CRO invoice when visit reaches Approved; PDF with procedure-level line items; invoice record stored in system |
| Sprint 7 | One-time fee invoicing: startup, archiving, pharmacy, administrative — billing triggers and invoice generation |
| Sprint 8 | Payment receipt tracking: mark invoice paid; payment date and amount recorded; cash position updated |
| Sprint 8 | Cash flow forecast: 13-week rolling forecast from scheduled visits + payment terms; 12-month strategic forecast with base/upside/downside scenarios |
| Sprint 8 | Patient reimbursement v1: travel claim submission (coordinator-entered); approval workflow; payment record |

Milestone M1.2: First automated investigator specification sent to Solimed investigators via Meridian — end Sprint 5 Milestone M1.3: First invoice auto-generated and tracked through to payment receipt — end Sprint 8

### Layer 3 — Clinical Operations (Sprints 5–12)

Goal: Full study/visit management replacing Power Apps coordinator UI. Coordinators use Meridian web app exclusively by end of Sprint 12.

| Sprint | Deliverables |
| --- | --- |
| Sprint 5 | Next.js app scaffold: auth, navigation, role-based menu, responsive layout |
| Sprint 5 | Studies list screen: create, view, search studies; CRO assignment; status (Draft/Open/On Hold/Stopped/Locked) |
| Sprint 6 | Site study setup: full configuration (investigators, visit budgets, one-time budgets, payment terms); site-level default budgets |
| Sprint 6 | Patient enrollment: add patient, assign ID, link to site study, initiate visit schedule |
| Sprint 7 | Visit logs — patient view: full coordinator dashboard; all visit statuses; visit date management; investigator assignment |
| Sprint 7 | Auto-scheduling at randomization: all protocol visits auto-populated from randomization date |
| Sprint 7 | Auto-skip on screen fail: future visits set to Skipped; study arm assignment for multi-arm protocols |
| Sprint 8 | Coordinator to-do dashboard: cross-study upcoming visits; overdue alerts; one-click status update |
| Sprint 8 | Visit tolerance warning system: colour-coded Green/Yellow/Red per tolerance window |
| Sprint 9 | Amendment handling: effective-from date on budget changes; multi-site amendment propagation; coordinator notification |
| Sprint 9 | Study show/stop controls: full lifecycle with auto-generated Stop Report |
| Sprint 9 | Bulk status operations: multi-visit select and update |
| Sprint 10 | Study progress summary card: % complete, % budget consumed, visits at risk |
| Sprint 10 | Normita & time tracking: time norms derived from visit budget; planned vs. actual hours; capacity heatmap |
| Sprint 11 | RBAC v1: Platform Admin / Site Admin / Coordinator / Investigator / Finance / Read-Only — enforced at API and UI |
| Sprint 11 | PII audit log: every patient data access and modification logged with user, timestamp, action |
| Sprint 12 | eSource v1: structured visit checklist; digital consultation report; timestamped + attributed entries; query management |
| Sprint 12 | Coordinator UAT sprint: 2–3 Solimed coordinators use Meridian for live visits; feedback incorporated |

Milestone M1.4: Coordinators conducting live Solimed visits in Meridian web app — end Sprint 12

### Layer 4 — Communication Hub (Sprints 9–14)

Goal: All patient communication — voice, SMS, video — flows through Meridian with AI transcription and clinical context.

| Sprint | Deliverables |
| --- | --- |
| Sprint 9 | Twilio integration: outbound/inbound voice calls from within patient record; call logged against patient |
| Sprint 10 | Real-time call transcription: live transcript during call; speaker labeling (Coordinator / Patient) |
| Sprint 10 | Post-call AI summary: key topics, action items, next steps — auto-generated via Claude API; linked to patient record and upcoming visit |
| Sprint 11 | SMS / MMS: two-way texting from patient record; TCPA-compliant opt-out; automated visit reminder templates |
| Sprint 11 | Automated visit reminders: SMS sent 48 hours before visit; pre-visit instructions; post-visit follow-up |
| Sprint 12 | Omnichannel inbox: unified view of all calls, SMS, emails per patient — chronological thread |
| Sprint 13 | Real-time coordinator coaching: AI surfaces protocol reminders during call (“Visit W144 due in 5 days — confirm appointment”); AE detection prompts |
| Sprint 13 | Screening call assistant: during screening calls, AI displays inclusion/exclusion criteria; prompts coordinator to ask each question; records responses |
| Sprint 14 | Sentiment analysis per patient: per-call sentiment score; sentiment trend over time; deteriorating engagement alert |
| Sprint 14 | Video visits: native video for Virtual visit types; recorded with consent; linked to visit record |
| Sprint 14 | CRO / sponsor communication channel: per-study channel for monitor communications; meeting intelligence (AI summary + action items) |

Milestone M1.5: First Solimed coordinator patient call conducted through Meridian with AI transcript and post-call summary — end Sprint 10

### Layer 5 — AI Intelligence (Sprints 11–18)

Goal: Predictive capabilities built on top of the operational data and communication data accumulated in Layers 1–4.

| Sprint | Deliverables |
| --- | --- |
| Sprint 11 | Backlog quality engine: stratify all backlog into Committed / Probable / At Risk / Excluded; quality % per study |
| Sprint 12 | Multi-arm backlog fix: backlog calculated only from patient’s assigned arm; unresolved arm alert |
| Sprint 13 | Enrollment velocity tracker: actual vs. target enrollment rate; projected completion date; revenue implication of off-pace enrollment |
| Sprint 13 | Protocol completion projection: per-patient visit forecast; study-level revenue curve for next 12 months |
| Sprint 14 | Revenue recognition dashboard: billable vs. at-risk vs. written-off split; screen fail revenue recognition |
| Sprint 14 | CRO performance scorecard: payment terms adherence, screen fail rate, margin per CRO |
| Sprint 15 | Dropout risk model v1: rule-based scoring using missed visits, overdue visits, sentiment trend, social determinants |
| Sprint 16 | Dropout risk model v2: ML model trained on Solimed’s historical visit + communication data; per-patient risk score with contributing factors |
| Sprint 16 | Patient qualification engine v1: run protocol eligibility criteria against Solimed’s patient database; ranked candidate list |
| Sprint 17 | Unit economics dashboard: revenue per patient, per visit, per coordinator hour; study type profitability |
| Sprint 17 | Coordinator performance intelligence: visit efficiency, protocol adherence rate, patient retention rate per coordinator |
| Sprint 18 | Predictive payment dashboard: cash flow prediction, CRO payment timing model, investigator payment forecast |
| Sprint 18 | Phase 1 hardening: full regression testing, security audit, performance testing at 10x Solimed volume |

Milestone M1.6: Dropout risk model live and scoring all 321 active Solimed patients — end Sprint 16 Milestone M1.7: Phase 1 complete — Solimed fully live on Meridian; all 5 layers operational — end Sprint 18

### Phase 1 Power BI Screens (Delivered Across Sprints 6–18)

| Screen | Sprint | Layer |
| --- | --- | --- |
| Enhanced P&L Dashboard | Sprint 6 | Layer 2 |
| Backlog Quality Dashboard v2 | Sprint 6 | Layer 5 |
| Normita & Time Dashboard | Sprint 6 | Layer 3 |
| Investigator Specification v2 | Sprint 6 | Layer 2 |
| Rolling 13-Week Cash Flow | Sprint 8 | Layer 2 |
| 12-Month Revenue Forecast | Sprint 8 | Layer 2 |
| Enrollment Velocity Tracker | Sprint 13 | Layer 5 |
| Protocol Completion Projection | Sprint 13 | Layer 5 |
| Revenue Recognition Dashboard | Sprint 14 | Layer 2 |
| CRO Performance Scorecard | Sprint 14 | Layer 5 |
| Unit Economics Dashboard | Sprint 17 | Layer 5 |
| Coordinator Performance | Sprint 17 | Layer 5 |

## 6. Phase 2 — Second Site (Months 10–15 / Sprints 19–30)

Goal: Prove multi-tenancy by onboarding a second SMO. AI models trained on Solimed data are applied to new site data. Validate the platform is a product, not a custom build.

### Target Second Site Criteria

- EU-based (GDPR already handled by platform)

- Small-to-mid SMO (5–20 active studies; 50–500 active patients)

- Different CRO mix from Solimed (validates CRO-agnostic approach)

- Ideally Drew Domescik network introduction or Solimed CRO referral

### Sprint Plan

| Sprint | Deliverables |
| --- | --- |
| Sprint 19 | Second site discovery: data model, current tools, pain points documented; onboarding checklist completed |
| Sprint 20 | Tenant provisioning: new tenant created in 48 hours via onboarding wizard; all configuration options available |
| Sprint 21 | Data migration: second site’s existing data imported to Meridian; validation complete |
| Sprint 22 | Localisation v1: i18n framework; locale-aware dates, numbers, currencies; second language added if required |
| Sprint 23 | Multi-currency engine: per-site currency config; FX rate integration (ECB API); historical rate preservation |
| Sprint 24 | Second country regulatory config: country-specific required fields; data residency in correct Azure region |
| Sprint 25 | Patient qualification engine v2: trained on combined Solimed + second site data; cross-tenant model (anonymised) |
| Sprint 26 | EHR integration pilot: FHIR R4 read from one EHR system used by second site (Epic or Cerner); patient profile enrichment |
| Sprint 27 | Recruitment pipeline v1: internal discovery (query patient database against protocol criteria); referral physician network management |
| Sprint 28 | Patient-facing pre-screening: public-facing questionnaire for study-specific pre-screening; qualified leads enter recruitment pipeline |
| Sprint 29 | eConsent module: digital ICF management; re-consent automation on amendment; 21 CFR Part 11 compliant |
| Sprint 30 | Phase 2 hardening: multi-tenant security audit; penetration testing; GDPR compliance review; Phase 2 sign-off |

Milestone M2.1: Second site tenant live and processing real studies — end Sprint 22 Milestone M2.2: First EHR-sourced patient identified as a qualified study candidate — end Sprint 26 Milestone M2.3: Security / penetration test passed — end Sprint 30

## 7. Phase 3 — Market Launch (Months 16–24 / Sprints 31–48)

Goal: Open Meridian to the market. Self-serve onboarding. Subscription billing. Target 5+ sites live by Month 24.

### Sprint Plan

| Sprint | Deliverables |
| --- | --- |
| Sprint 31–32 | Self-serve onboarding wizard: new site completes setup without Pivot involvement; all config screens; guided flow |
| Sprint 33 | Subscription billing: Stripe integration; per-site/per-study tier pricing; automated invoicing to customers; usage metering |
| Sprint 34 | Customer admin portal: site admins manage their own users, studies, CRO connections, billing |
| Sprint 35–36 | CRO portal: CRO-facing read-only view of all their studies across all Meridian sites; live visit status; payment specs |
| Sprint 37 | Recruitment engine v2: digital intake forms (public landing pages); campaign lead capture; pipeline conversion tracking; diversity monitoring |
| Sprint 38 | External registry integration: connect to 1–2 disease registries; opt-in patient discovery from registry data |
| Sprint 39 | Regulatory intelligence v1: country regulatory change monitoring; alert when a change affects active studies on the platform |
| Sprint 40 | Mobile app v1 (React Native): coordinator schedule view; visit check-in/out; offline visit logging with sync |
| Sprint 41 | Mobile app v2: investigator app; push notifications; e-signature on mobile |
| Sprint 42 | AI model marketplace: sites can enable/disable AI features per study; model performance dashboards |
| Sprint 43–44 | Protocol deviation AI: real-time detection of deviations from protocol schedule; deviation classification (minor vs. major); CRO notification workflow |
| Sprint 45 | Document management: version-controlled doc store per study; expiry tracking; e-signature via DocuSign API |
| Sprint 46 | Sponsor-facing dashboard: sponsor view of their study performance across all Meridian sites (read-only; separate from CRO portal) |
| Sprint 47 | Platform hardening: SOC 2 Type II readiness audit; HIPAA BAA documentation; performance testing at 50-site scale |
| Sprint 48 | Market launch: public website live; 5+ sites onboarded; press / industry announcement |

Milestone M3.1: First self-serve site onboarded without Pivot involvement — end Sprint 32 Milestone M3.2: 5 sites live on Meridian — end Sprint 40 Milestone M3.3: Mobile app in App Store and Google Play — end Sprint 41 Milestone M3.4: SOC 2 Type II audit initiated — end Sprint 47 Milestone M3.5: Public market launch — end Sprint 48

## 8. Team Structure

### Core Product Team

| Role | Phase 1 FTE | Phase 2 FTE | Phase 3 FTE | Responsibilities |
| --- | --- | --- | --- | --- |
| Product Manager | 1.0 | 1.0 | 1.0 | Product vision, roadmap, backlog, stakeholder alignment |
| Technical Lead / Architect | 1.0 | 1.0 | 1.0 | Architecture decisions, code quality, ADRs, security |
| Full-Stack Developer | 2.0 | 2.0 | 3.0 | API, frontend, database, integrations |
| Data / BI Engineer | 0.5 | 1.0 | 1.0 | Power BI, data pipeline, Layer 1 ingestion adapters |
| ML Engineer | 0.5 | 1.0 | 1.0 | Layer 5 models: qualification, dropout risk, revenue prediction |
| Mobile Developer | 0 | 0.5 | 1.0 | React Native iOS/Android app (Phase 3) |
| QA Engineer | 0.5 | 1.0 | 1.0 | Test strategy, automation, regression, security testing |
| UX Designer | 0.5 | 0.5 | 0.5 | Coordinator / investigator workflows, usability testing |
| DevOps / Infrastructure | 0.25 | 0.5 | 0.5 | Azure, CI/CD, monitoring, compliance infrastructure |

### Solimed Team (Phase 1 Only)

| Name | Role | Availability |
| --- | --- | --- |
| Mladen Geng | Domain Expert / Knowledge Transfer | 2 days/week Sprints 1–2; then ad-hoc |
| Ivan Kruljac | Product Sponsor | Sprint reviews + strategic decisions |
| Drew Domescik | CFO Advisor / Financial Features Sponsor | Sprint reviews + financial UAT |
| 2–3 Coordinators | End User Testers | Sprint 12 UAT; periodic usability sessions |
| Finance Role (TBD) | Billing Workflow SME | Sprint 5–8 billing UAT |

## 9. Risk Register

| # | Risk | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Mladen unavailable — knowledge transfer incomplete | Med | Critical | Sprint 1 is 100% knowledge transfer; record all sessions; document everything before building |
| R2 | Solimed data quality worse than expected | Med | High | Data audit in Phase 0; clean before migrating; do not migrate garbage |
| R3 | Power Apps limitations block Layer 3 UI parity | Med | High | Power Apps UI stays live in parallel until Meridian UI is UAT-approved by coordinators |
| R4 | Twilio HIPAA-eligible configuration complexity | Low | High | Engage Twilio enterprise team in Sprint 9; validate BAA before any patient calls go through |
| R5 | EHR FHIR integration access denied by hospital IT | High | Med | FHIR stub in Layer 1 Sprint 4; EHR integration is Phase 2 — not on critical path for Phase 1 |
| R6 | Claude API (call summaries) cost at scale | Med | Med | Token usage monitoring from Sprint 10; set per-call token budget; evaluate caching summaries |
| R7 | ML model accuracy insufficient for clinical trust | Med | High | Models start rule-based (Sprint 15); ML layer (Sprint 16) is additive — rules are always the fallback |
| R8 | Second site not identified by Month 10 | Med | High | Begin second site outreach at Month 6; Drew’s network; Solimed CRO introductions |
| R9 | Regulatory requirements in second country unknown | High | High | Regulatory scan begins Phase 1 Sprint 14; legal counsel engaged before Phase 2 |
| R10 | Key Pivot team member departure | Low | High | Pair programming standard; all code reviewed; ADRs documented; no single-person knowledge silos |
| R11 | Scope creep from Solimed (treating Meridian as custom dev) | High | Med | Clear distinction: Solimed is a platform customer, not a custom dev client; change requests evaluated against platform fit |
| R12 | Competing platform (Crio, Florence) copies AI features | Med | Med | Speed of execution; network effects (more sites = better AI models); Solimed reference customer |
| R13 | Data privacy breach (patient data) | Low | Critical | Security audit Phase 1 Sprint 18; pen test before Phase 2; HIPAA BAA all services; PII audit log from Sprint 11 |

## 10. Technology Decision Log

All architecture decisions recorded as ADRs in the GitHub repository at docs/adr/. Decisions made in Phase 0 Week 2 and frozen for Phase 1.

### Pre-decided (from platform vision)

| Component | Decision | Rationale |
| --- | --- | --- |
| Frontend | Next.js (React) | SSR performance; React Native code sharing |
| API | Node.js (Fastify) or Python (FastAPI) | To be decided Week 2 |
| Database — primary | PostgreSQL on Azure | Relational; ACID; HIPAA-capable |
| LLM | Claude API (Anthropic) | Call summaries, protocol extraction, AI coaching |
| Communications | Twilio | Programmable; HIPAA-eligible voice + SMS |
| Video | Daily.co | HIPAA-compliant video; embed in web app |
| Reporting | Power BI Embedded | Solimed compatibility; best-in-class BI |
| Auth | Auth0 or Azure AD B2C | To be decided Week 2 |
| Infrastructure | Azure | Microsoft ecosystem; HIPAA BAA; global regions |
| CI/CD | GitHub Actions | Free tier sufficient; in-repo workflows |
| Search / eligibility matching | Elasticsearch | Full-text + structured query; protocol criteria matching |
| Payments (platform billing) | Stripe | Industry standard; subscription metering |
| E-signature | DocuSign API | eConsent and document signing |

## 11. Quality Gates

Every phase has a quality gate that must pass before the next phase begins:

### Phase 1 → Phase 2 Gate

- All 5 layers operational for Solimed in production

- Zero critical or high security findings from Phase 1 audit

- Coordinator NPS ≥ 40 (3+ coordinators surveyed)

- Automated investigator spec sending running without errors for 2+ consecutive months

- All Solimed data migrated; Power Apps decommissioned or in read-only mode

- Ivan Kruljac written sign-off on Phase 1 completion

### Phase 2 → Phase 3 Gate

- Second site live and processing real studies

- Penetration test passed (no critical/high findings)

- GDPR compliance review passed for both countries

- Patient qualification engine scoring candidates at second site

- Solimed site-specific dropouts predicted with >65% accuracy (30-day look-ahead)

- Self-serve onboarding wizard complete and tested

### Phase 3 Launch Gate

- 5 sites live on platform

- SOC 2 Type II audit initiated

- Mobile app in App Store and Google Play

- No P1 incident in prior 30 days

- All customer SLAs met for 60 consecutive days

## 12. Communication & Governance

### Cadences

| Meeting | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Sprint Planning | Bi-weekly (Monday) | Full Pivot team | Sprint backlog commitment |
| Daily Standup | Daily | Pivot team | Blockers, progress, dependencies |
| Sprint Review | Bi-weekly (Friday) | Pivot + Ivan + Drew | Demo working software; get feedback |
| Product Steering | Monthly | Pivot PM + Ivan + Drew | Roadmap, priorities, budget |
| Architecture Review | Monthly | Pivot Tech Lead + Pivot PM | ADR review; technical debt; scaling decisions |
| Retrospective | Bi-weekly | Pivot team only | Process improvement |

### Reporting

| Report | Frequency | Audience | Contents |
| --- | --- | --- | --- |
| Sprint Summary | Bi-weekly | Ivan, Drew | Completed features, velocity, next sprint plan, risks |
| Product Metrics Dashboard | Monthly | Ivan, Drew, Pivot leadership | Active users, visits processed, AI model performance, ARR pipeline |
| Financial Tracker | Monthly | Ivan | Pivot hours consumed, budget remaining, Phase forecast |
| Risk Register Update | Monthly | Ivan | New risks, mitigated risks, open items |

## 13. Success Metrics

### Phase 1 Metrics (Solimed as design partner)

| Metric | Target | Measurement |
| --- | --- | --- |
| Coordinator adoption | 100% of Solimed coordinators using Meridian daily | Login tracking |
| Visit logging accuracy | Same or better than Power Apps (zero regression) | Comparison audit Sprint 12 |
| Investigator spec automation | Monthly spec emails sent without manual intervention | Email send logs |
| Backlog accuracy | Multi-arm inflation resolved; ≤5% variance from manual calculation | Finance reconciliation |
| Coordinator NPS | ≥40 | Post-Phase-1 survey |
| AI call summary quality | Ivan + coordinator rating ≥4/5 on 20+ summaries | Manual rating survey |
| Dropout prediction accuracy | >60% precision on 30-day dropout flag | Retrospective model evaluation |

### Phase 2 Metrics (Second site)

| Metric | Target |
| --- | --- |
| Onboarding time for second site | <2 weeks from data import to first live visit |
| Patient qualification engine | >70% of top-10 candidates pass formal screening |
| EHR-sourced candidates | >20% of screening patients sourced via EHR integration |

### Phase 3 Metrics (Market)

| Metric | Target |
| --- | --- |
| Sites live | 5+ by Month 24 |
| ARR | €150K+ by Month 24 (ramp toward €600K Year 3 target) |
| Self-serve onboarding | New site live in <48 hours without Pivot involvement |
| Churn | <10% annual site churn |
| NPS (all customers) | ≥50 |

This PM plan is a living document. It will be updated at the start of each phase based on what was learned in the prior phase. The sprint-level detail for Phase 2 and Phase 3 will be refined as Phase 1 progresses.